## Sheet1
Date (to write in) | Day # in EA | Sections and tasks to do | in which households | DIARIES
| 1 | arrive, meet the officials, find households |  | HH 1-6 | HH 7-12
| 2 | 1, 2, 18 | 1-4
| 3 |  | 5-8
| 4 |  | 9-12
| 5 | 17, introduce Week 1 diary | 1-6
| 6 |  | 7-12 | day 1 for Wk 1 diary
| 7 | 3, 4, 5, 6, and review first day of diary | 1-6 | day 2 for Wk 1 diary | day 1 for Wk 1 diary
| 8 |  | 7-12 | day 3 for Wk 1 diary | day 2 for Wk 1 diary
| 9 | 7,8,9 and review diary, give week 2 diary to be ready | 1-4 | day 4 for Wk 1 diary | day 3 for Wk 1 diary
| 10 |  | 5-8 | day 5 for Wk 1 diary | day 4 for Wk 1 diary
| 11 |  | 9-12 | day 6 for Wk 1 diary | day 5 for Wk 1 diary
| 12 | catch up anything not done |  | day 7 for Wk 1 diary | day 6 for Wk 1 diary
| 13 | 10, 19, pick up and review week 1 diary,make sure HH's starting week 2 diary today | 1-6 | day 1 for Wk 2 diary | day 7 for Wk 1 diary
| 14 |  | 7-12 | day 2 for Wk 2 diary | day 1 for Wk 2 diary
| 15 | 11, 12, 13, 14 (men), 16, 20, check diaries | 1-4 | day 3 for Wk 2 diary | day 2 for Wk 2 diary
| 16 |  | 5-8 | day 4 for Wk 2 diary | day 3 for Wk 2 diary
| 17 |  | 9-12 | day 5 for Wk 2 diary | day 4 for Wk 2 diary
| 18 | correct errors, finish any modules pending |  | day 6 for Wk 2 diary | day 5 for Wk 2 diary
| 19 |  |  | day 7 for Wk 2 diary | day 6 for Wk 2 diary
| 20 | 14 (woman) , 15 (women) , collect and review Wk 2 dairies, finish any modules pending | 1-6 |  | day 7 for Wk 2 diary
| 21 |  | 7-12
| 22 | finish in EA, document everything